## Intro
Welcome
Please read the following instructions and background information before using the calculator
Why was this calculator produced?
This HIA calculator was originally developed by the London Health Observatory (now incorporated within Public Health England). In order to respond to requests from practitioners who were looking for tools to enable them to undertake HIAs, the NCCHPP received permission from the London Health Observatory to adapt it for use in the Canadian context. The question “How much does an HIA cost?” is difficult to answer precisely as the nature of specific policies, programs and projects are so varied (as too are relative scales of the HIAs proposed for them). This calculator is designed to assist those who are considering an HIA to estimate the time, money and human resources required for the tasks to be performed in an HIA process. The calculator provides suggestions about what to consider when planning for HIA. The times and estimated costs are by no means exhaustive, but those planning HIAs are better served by a ballpark figure as a starting point rather than being told that a figure cannot be given because HIAs vary so much! The calculator is best suited to those planning HIAs rather than those who have done them many times before and who could therefore base their estimates on personal experience.
Often very tight timelines mean that extra capacity such as consultants or other externally-commissioned individuals have to be bought in to lead the HIA process or to get involved in one or more specific components of the HIA (e.g., for some or all of the appraisal process). In addition to that, while many tasks do not generate external costs, they may require considerable staff time (e.g., coordinating the HIA process; gathering information, communicating with others, and providing administrative support). It is important to factor in these internal opportunity costs to an organization as well.
What will the calculator help you to do?
The HIA calculator will take you through each stage of an HIA, helping you to decide:
· What tasks are required at each stage;
· Who might be involved in doing them;
· The amount of time that these tasks may take;
· Salary costs for those involved;
· Other costs to consider.
Using this calculator will lead you to a summary page listing the time and money that your HIA will require (organized by steps, as well as a grand total)
Instructions for how to use the calculator
1. Open the ‘Assumed costs’ tab (see the different tabs along the bottom of this sheet) and enter the hourly salaries for the people who will be involved in your HIA.
2. Move onto the 'Screening' tab. Drop-down menus are available for listing some of the tasks and activities. These are expressed as suggested time necessary (in hours) for each person likely to be involved during this step. The 3 choices correspond to the estimated hours required for that person’s involvement in that particular task during a rapid, intermediate or comprehensive (small, medium or large-scale) HIA. You can enter your own estimate here. You also have the choice of whether to have an internal staff member or external consultant perform each task. The choices given in the drop down menu are for total hours needed for that task (allocated to internal staff members). If you decide that some of that time will be allocated to an external person, subtract the estimated hours from the internal individual and enter it in the appropriate cell for the external individual. Other costs should be entered for venue and catering costs as appropriate.
3. Move through each of the other stages of HIA in the same fashion
4. If you find that you must stop to gather more information, or pause for whatever reason, you can download the calculator and complete it at your leisure.
Steering Group Meetings
A steering group is the project group working on the HIA. (A steering group will give advice and review the HIA, and take part in some of its steps such as screening, drawing a logic model, collecting some data, deciding on what recommendations should be made, and more.) It is likely that a total of 2-6 meetings for this group will be required for an entire HIA. The majority of the steering group costs will probably be in-kind and will not be borne by the organization conducting an HIA, because the committee members will probably be donating their professional or personal time. It is still worthwhile to consider these in-kind costs associated with steering committee meetings in order to determine the ‘true costs of HIA’. Administration will be required for these meetings in order to organize logistics and prepare documents as needed. Steering group members are often requested to proofread the various documents prepared during the appraisal stage of the HIA (as well as the final report). They will also need to travel to the meeting venue which may cost time and money. These activities (and the number of people on the steering group) should be considered when deciding how much time and money to budget for this component. Due to the individual nature of this aspect, ‘steering group meetings’ have been listed as an additional cost. One could expect that each meeting would take a half day of the HIA lead’s time and a half day of administrative time. Keeping this information in mind, there is a space for estimating steering group costs for each stage in the HIA.
Internal lead - a person commissioned to do all (or parts) of the HIA. Any tasks that are outsourced can be categorized as External Consultant in the calculator.
Internal Administrator - the person providing administrative support for the HIA. It is unlikely that this person's work would be outsourced.
Internal Researcher - this refers to any internal staff member who contributes to the HIA. For example, an information analyst or community development worker.
External Consultant - this can refer to the person assuming any outsourced portions of the internal lead's role, or other tasks that would have similar costs per hour.
External Researcher - this refers to any individual external to the organization who may need to be paid for contributing time toward the HIA. Examples are a community development worker who may collect views from the affected communities or a public health student who conducts some information analysis or other task as part of the HIA process.
Disclaimer
This HIA calculator is a tool to guide HIA planners. The National Collaborating Centre for Healthy Public Policy (NCCHPP) takes no responsibility for any results obtained by using this calculator, nor for any uses to which those results are applied.
Next

## Assumed Costs
Instructions
Please enter the salary (cost per hour) per person
This amount will then be used to calculate the costs associated with various tasks throughout the calculator
Type | Cost per hour | Explanation
Internal Lead | 0 | Use hourly rate.
Internal Researcher | 0 | The term 'researcher' is used here to refer to any staff member who will contribute to the HIA process. For example, an information analyst or community development worker. Use hourly rates
Internal Administrator | 0 | Use hourly rate.
External Consultant | 0 | If needed
External Researcher | 0 | If needed for activities such as analysis, literature reviews, etc. It may be possible to solicit the help of volunteers for some tasks.
|  | Back | Next

## Screening
Cells with a red arrow, located on the upper right hand side, indicate suggested times.
Please note that the suggested times given are a rough guide only. HIAs will vary considerably in the amount of time required for each task.
Assumption: 1 day = 7 hours
Where there are no suggested times given, as this person won't always conduct the task, it may be that some of the intended time for the ‘HIA lead’ will be delegated to this person.
In this case, this quantity of hours should be deducted from the ‘Internal Lead’ cell.
(1) Screening
Screening is the first stage of a HIA and acts as a selection process where proposals are quickly 'screened' for their potential to affect the population's health. It helps determine whether an HIA is needed or not, and if needed, it considers the opportunity for influencing decision making. In screening, we also identify which determinants of health will be most likely significantly affected by the proposal, and select our priorities for the next steps. Vulnerable populations with respect to these impacts are also identified. Often a screening checklist is used to aid this process. Click on the following link to view some examples: http://www.health.govt.nz/publication/whanau-ora-health-impact-assessment-2007.
|  | Internal Lead | Internal Researcher | Internal Admin | External Consultant | External Researcher | Additional Cost
(1) Screening | [6 empty] | Type | Cost ($)
Gaining Familiarity | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Applying tool | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Administration | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Total Hours |  | 0 | 0 | 0 | 0 | 0
Activity Cost |  | 0 | 0 | 0 | 0 | 0 |  | 0
Total Screening Cost | 0 | [7 empty] | Back | Next
Total Screening Time (Hrs) | 0
Gaining familiarity | Time is required to read documentation pertaining to the proposal and speak with people who have information which would help you determine whether an HIA is necessary. At what stage of the decision-making process is the proposal? Who could you engage to participate in the screening process to ensure maximum buy-in?
Applying tool | This process could be benefited by the involvement of others. Whose proposal is it? Whose support would you need if you were to conduct an HIA? Together, you will then look at the proposal and select the determinants of health that you think will most likely be affected significantly by the proposal. Vulnerable populations with respect to the distributions of impacts are also identified.
Administration | Time will be required for preparing copies of documents and arranging meetings
Note on C16: Suggested Time Taken: Rapid - 1 Hour Intermediate - 4 Hours Comprehensive - 1 Day
Note on C21: Suggested time taken Rapid - 2 Hours Intermediate: 2 Hours Comprehensive: 1 Day
Note on C26: Suggested Time Taken: Rapid - 1 Hour Intermediate - 2 Hours Comprehensive - 3½ Hours

## Scoping
Cells with a red arrow, located on the upper right hand side, indicate suggested times.
Please note that the suggested times given are a rough guide only. HIAs will vary considerably in the amount of time required for each task.
Assumption: 1 day = 7 hours
Where there are no suggested times given, as this person won't always conduct the task, it may be that some of the intended time for the ‘HIA lead’ will be delegated to this person.
In this case, this quantity of hours should be deducted from the ‘Internal Lead’ cell.
(2) Scoping
Scoping sets the boundaries for the HIA and establishes a firm foundation for the next steps, beginning with the appraisal.
It can be divided into two parts: scoping of the issues and scoping of the process. In the scoping of the issues, your hypothesis concerning the link between the proposal
and the health of the population affected will have to be made explicit in a logic model.
The scoping of the process is the project management component of HIA where the various tasks required for an HIA are planned.
(2) Scoping |  | Internal Lead | Internal Researcher | Internal Admin | External Consultant | External Researcher | Additional Cost
[7 empty] | Type | Cost ($)
Establishing a Steering Group | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Preliminary Answers to Scoping Questions and Drawing a Logic Model | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Steering Group Meetings During This Phase | Insert Estimate(Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Total Hours |  | 0 | 0 | 0 | 0 | 0
Activity Cost |  | 0 | 0 | 0 | 0 | 0 |  | 0
Total Scoping Cost | 0
Total Scoping Time (Hrs) | 0
Establishing a Steering Group | A steering group or management group for the scoping phase is often appointed to oversee the process and outputs of an HIA at the scoping stage, and comprises representatives from key stakeholder organizations and, ideally, representatives from the communities affected. It sometimes includes one or more of the decision makers whose proposal is the subject of the HIA. | [7 empty] | Back | Next
A steering group should be convened once it has been decided that an HIA is necessary and value added. Its functions will be to:
• Set the scope for the HIA;
• Support the development of the logic model;
• Set the format of and questions to be addressed at the stakeholder workshop;
• Suggest participants to be invited to the stakeholder workshop; and
• Plan out the final report.
As a general rule, a steering group should have no more than 12 people on it. It is important to think about ‘representativeness’: involving senior post holders with decision-making powers, those with access to - and who can bring in - stakeholder views, and individuals who can take on tasks to contribute to completing the HIA.
Answering scoping questions
Clarity is required at the scoping stage with respect to the following topics:
• Timescale for the analysis of impacts,
• Geographical boundaries,
• Population covered,
• Explicit hypothesis concerning potential health affects/impacts of concern - logic model,
• Criteria for prioritization of health impacts,
• Methods of appraisal,
• The various stakeholders and the nature of their participation,
• Management arrangements for the appraisal, including the appointment of the assessor (whether internal or external) and the mechanism for managing the assessors, including feedback process,
• Work programme - including timetable, deadlines, outputs (including conditions about ownership, confidentiality & copyright),
• Resources - including budget & sources of funding, personnel & facilities,
• Responsibility for decision making,
• Responsibility for monitoring evaluation as well as evaluating proposal implementation, process & health outcomes.
Steering Group Meetings | The number of steering group meetings required during the scoping phase is likely to be 1, 2 or 3 for rapid, intermediate and comprehensive HIAs respectively. (See Steering Group meetings on the Introductory Page)
Note on C16: Suggested Time Taken: Rapid - 1 Hour Intermediate - 2 Hours Comprehensive - 4 Hours
Note on C21: Suggested Time Taken: Rapid - 3½ Hours Intermediate - 1 Day (7 Hours) Comprehensive - 2 Days (14 Hours)

## Recommendations
Cells with a red arrow, located on the upper right hand side, indicate suggested times.
Please note that the suggested times given are a rough guide only. HIAs will vary considerably in the amount of time required for each task.
Assumption: 1 day = 7 hours
Where there are no suggested times given, as this person won't always conduct the task, it may be that some of the intended time for the ‘HIA lead’ will be delegated to this person.
In this case, this quantity of hours should be deducted from the ‘Internal Lead’ cell.
(4) Recommendations
This stage comes after many different types of evidence have been collected and prioritized. The recommendations, which are the main outputs of the HIA process, are specifically made to inform decision makers. Given their importance, thought should be given to how to group and rank them. Draft recommendations should be reviewed by decision makers prior to delivery. One should also consider how to convey or deliver the information by the means most suitable for the decision makers in question.
(4) Recommendations |  | Internal Lead | Internal Researcher | Internal Admin | External Consultant | External Researcher | Additional Cost ($)
Formulating Recommendations | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0
Report Writing | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0
Total Hours |  | 0 | 0 | 0 | 0 | 0
Activity Cost |  | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Back | Next
Total Recommendations Cost | 0
Total Recommendation Time (Hrs) | 0
Formulating Recommendations |  | This is usually done by the report author in conjunction with one or more (or perhaps all) members of the steering group. Some criteria for prioritizing them may need to be adopted if there are many recommendations and conflicting views.
Report Writing |  | The final report containing the recommendations is usually written by the HIA lead or project manager. Time should be factored in for the steering group to review the final draft, and for incorporating their suggestions into the final version.
Note on C17: Suggested Time Taken: Rapid - 1 Day (7 Hours) Intermediate - 2 Days (14 Hours) Comprehensive - 3 Days (21 Hours)
Note on C20: Suggested Time Taken: Rapid - 5 Days (35 Hours) Intermediate - 8 Days (56 Hours) Comprehensive - 14 Days (98 Hours)
Note on E20: Suggested Time Taken: Rapid - 3½ Hours Intermediate - 1 Day (7 Hours) Comprehensive - 2 Days (14 Hours)

## Appraisal
Cells with a red arrow, located on the upper right hand side, indicate suggested times.
Please note that the suggested times given are a rough guide only. HIAs will vary considerably in the amount of time required for each task.
Assumption: 1 day = 7 hours
Where there are no suggested times given, as this person won't always conduct the task, it may be that some of the intended time for the ‘HIA lead’ will be delegated to this person.
In this case, this quantity of hours should be deducted from the ‘Internal Lead’ cell.
(3) Appraisal
In the appraisal stage of HIA, the process moves towards practical outputs. It is the stage where many different types of evidence are collected from the scientific and grey literatures, other data, and from consultation with individuals and groups. It involves investigating, appraising and reporting on how the proposal's implementation is likely to affect the health of populations. The health impacts (positive and negative) of a proposal are identified by stakeholders and/or assessors. Rapid and intermediate HIAs use existing data.
(3) Appraisal |  | Internal Lead | Internal Researcher | Internal Admin | External Consultant | External Researcher | Additional Cost ($)
[7 empty] | Type | Cost($)
Proposal Analysis | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Community Profile | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Expert consultation | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Literature Review and Data analysis | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Stakeholder/ Community Participation Workshop | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
Steering Group Meetings at this Stage | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | Venue | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0 | Travel | 0
[7 empty] | Catering | 0
[7 empty] | Other | 0
[9 empty] | Back | Next
Total Hours |  | 0 | 0 | 0 | 0 | 0
Activity Cost |  | 0 | 0 | 0 | 0 | 0 |  | 0
Total Appraisal Cost | 0
Total Appraisal Time (Hrs) | 0
Proposal Analysis | Proposal analysis identifies and examines key aspects of the proposal to inform the identification and characterization of the potential effects on health.
Community Profile | Compiling a community profile is useful in gaining a better understanding of the characteristics of people living in a particular area. The information that a community profile provides helps identify specific health needs and vulnerabilities of the groups it covers. The time required for compiling a community profile depends on what is immediately available.
Expert Consultation | Experts in specific domains could be helpful in provinding accurate scientific knowledge on potential impacts, on possible scenarios to avoid negative impacts or on how to maximize positive impacts
Literature Review and Data Analysis | The literature review includes gathering data on potential health impacts as well as impacts identified in previous HIAs. Data includes primary, secondary and grey literatures. Literature review evidence guidelines are systematically developed statements to support practitioners during the HIA process. Where an existing, recent, high-quality review is available, it may only need updating. Quantitative data analysis can also be undertaken in HIAs where epidemiological data can be modelled to predict health impacts of changes to a determinant of health. Human resources will depend on the time and money available (limits may be defined either by those who commissioned the HIA or by the organization conducting it). Literature reviews can be brief or comprehensive and can range from brief (2 days) to those involving several people over weeks to 18 months depending on the available resources and the degree of complexity.
Stakeholder/ Community Participation Workshop | A stakeholder meeting enables wider community participation in the appraisal stage. Stakeholders contribute to the process and the outcomes of an HIA, by contributing their views and by taking some ownership of the process. A stakeholders’ or ‘community participation’ workshop aims to bring together affected community members and stakeholders. By way of a facilitated workshop, views can be shared (and documented) about how a proposal might affect the health of communities. Attendees can offer their own experiences and help to appraise the evidence already collected. This process can help to inform recommendations that come out of the HIA. The recommended number of attendees at a stakeholder meeting during the appraisal stage is around sixty. One facilitator for every 10 participants is recommended.
Steering group meetings during this stage | See the note about steering group meetings on the introductory page for guidance on budgeting for these. The number of steering group meetings required during the appraisal stage is likely to be 1 or 2.
Note on C16: Suggested Time Taken: Rapid - 3 Hours Intermediate - 10 Days (70 Hours) Comprehensive - 14 Days (98 Hours)
Note on C21: Suggested Time Taken: Rapid - 1 Day (7 Hours) Intermediate - 12 Days (84 Hours) Comprehensive - 14 Days (98 Hours)
Note on C31: Suggested Time Taken Rapid - 2 Hours Intermediate - 3 days (21 Hrs) Compréhensive - 7 days (49 Hrs)
Note on C36: Suggested Time Taken: Rapid - 3 Days (21 Hours) Intermediate - 5 Days (35 Hours) Comprehensive - 15 Days (105 Hours)

## Further Engagement
(5) Further Engagement
Spending time networking with decision makers after the final report has been submitted can help to reinforce the value of the evidence-informed recommendations & encourage them to adapt their proposal accordingly. One steering group meeting should be planned-for during this stage. See the section on steering group meetings in the introduction for guidance about budgeting.
(5) Further Engagement |  | Internal Lead | Internal Researcher | Internal Admin | External Consultant | External Researcher | Additional Cost ($)
Including Steering Groups
| Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0
Total Hours |  | 0 | 0 | 0 | 0 | 0
Activity Cost |  | 0 | 0 | 0 | 0 | 0 | 0
Total Further Engagement Cost | 0
Total Further Engagement Time (Hrs) | 0
[8 empty] | Back | Next

## Evaluation
Cells with a red arrow, located on the upper right hand side, indicate suggested times.
Please note that the suggested times given are a rough guide only. HIAs will vary considerably in the amount of time required for each task.
Assumption: 1 day = 7 hours
Where there are no suggested times given, as this person won't always conduct the task, it may be that some of the intended time for the ‘HIA lead’ will be delegated to this person.
In this case, this quantity of hours should be deducted from the ‘Internal Lead’ cell.
(6) Evaluation
Monitoring and evaluation can offer valuable insights into how to improve the process of HIA and modify various proposals to achieve health gains. Assessing the accuracy of predictions made during appraisal is complex and requires a longer time frame, so outcome evaluation is not considered here. There are two main types of evaluation that can be conducted following the assessment and implementation of the proposal, relating to the HIA process and to the impact of the process on decision making.
|  | Internal Lead | Internal Researcher | Internal Admin | External Consultant | External Researcher | Additional Cost ($)
(6) Evaluation
Process | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0
Impact | Insert Estimate (Hrs) | 0 | 0 | 0 | 0 | 0 | 0
| Cost (per hour) | 0 | 0 | 0 | 0 | 0
Total Hours |  | 0 | 0 | 0 | 0 | 0
Activity Cost |  | 0 | 0 | 0 | 0 | 0 | 0
Total Evaluation Cost | 0 | [6 empty] | Back | Next
Total Evaluation Time (Hrs) | 0
Process | This involves evaluating how successful the process of carrying out the HIA was in practice. It is important as a source of learning, for quality improvement and for quality assurance. It could be as rapid as revisiting the original HIA aims and objectives and self-assessing whether these were met.
Impact | This involves assessing whether the recommendations are incorporated into the final proposal. It monitors the acceptance of recommendations and, once accepted, their implementation. The time required depends on how able one is to repeat the evaluation at intervals in order to follow the evolution of the proposal over time. Time should be allocated for an HIA practitioner and the administrative person. The span of time for monitoring these impacts could range from 1 day to weeks.
Note on C19: Suggested Time Taken: Rapid - 1½ Days (10.5 Hours) Intermidiate - 2½ Days (17.5 Hours) Comprehensive - 3½ Days (24.5 Hours)
Note on D19: Suggested Time Taken: 0 Hours
Note on E19: Suggested Time Taken: Rapid - 3½ Hours Intermediate - 1 Day (7 Hours) Comprehensive - 1½ Days (10.5 Hours)
Note on C22: Suggested Time Taken: Rapid - 1½ Days (10.5 Hours) Intermediate - 2½ Days (17.5 Hours) Comprehensive - 3½ Days (24.5 Hours)
Note on D22: Suggested Time Taken: 0 Hours
Note on E22: Suggested Time Taken: Rapid - 3½ Hours Intermediate - 1 Day (7 Hours) Comprehensive - 1½ Days (10.5 Hours)

## HIA Total costs
| Internal |  | External |  | Additional Costs
| Hours | Cost ($) | Hours | Cost ($) | ($)
(1) Screening | 0 | 0 | 0 | 0 | 0
(2) Scoping | 0 | 0 | 0 | 0 | 0
(3) Appraisal | 0 | 0 | 0 | 0 | 0
(4) Recommendations | 0 | 0 | 0 | 0 | 0
(5) Further Engagement | 0 | 0 | 0 | 0 | 0
(6) Evaluation | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0
Total Hours | 0
Total Cost | 0 |  |  |  |  | Back

## _Options (hidden)
HIA | HIA | HIA
INTERNAL | INTERNAL | INTERNAL
EXTERNAL | EXTERNAL | EXTERNAL